## EVENT Risk Register Template
Event Risk Register and Risk Control Plan
Event Name: |  |  |  | Event Location:
Event Date: |  |  |  | Expected Attendance:
Event Times: |  |  |  | Date Register Completed:
RISK ASSESSMENT
|  |  |  | RISK ASSESSMENT (risk level BEFORE your risk controls are in place) | [5 empty] | RESIDUAL RISK ASSESSMENT (risk level AFTER your risk controls are in place)
Source | Hazard / Aspect | Un-wanted Event (what could go wrong?) | Does this risk apply to your event? Choose Yes or No | Consequence | Likelihood | Risk Level | Rank | RISK CONTROLS (delete or add to this example list) | RESPONSIBILITY (Person/s responsible for managing control) | Consequence | Likelihood | Risk Level | Rank | Risk Tolerance Yes or No or ALARP
EXAMPLE 1: Event Site | Slip and Trip Hazards | • Injury to patron from uneven ground, slippery and wet surfaces, objects, curbs, ledges. | Yes | 3-Moderate | C-Possible | Medium | 9 | • City Parks Officers to inspect the reserve prior to the event • Thorough assessment of site is undertaken prior to event and ditches / uneven ground is filled in to minimise risk of tripping • Sufficient flood lighting is provided car park, vehicle drop off point, walkways and around facility • Event Manager, Site Manager, Safety Officer and all staff/volunteers briefed to ensure trip hazards are identified and action taken to rectify problem • Pathways and thoroughfares kept free of trip hazards • Use licensed electrical contractors to hang overhead power lines where possible • Cable trays and rubber matting covers will be utilised to cover cable runs • First Aid Officer present |  | 3-Moderate | D-Unlikely | Medium | 6 | ALARP
EXAMPLE 2: Event Site | Electric Shock or Electrocution | • Overhead power lines - electrocution injuries to staff or participants if machinery or amusement ride contacts overhead power lines • Exposed electrical cables • Electric shock caused by striking underground electrical cable during marquee set up. | Yes | 5-Severe | D-Unlikely | High | 10 | • Obtain and comply with necessary permits, approvals and licenses, legislation, standards and guidelines issued by Council and other government agencies • Site Plan includes location of power source Works and Services to paint location of underground reticulation • Map of underground services provided to event organiser to specify exclusion zone • Install appropriate signage advising of electrical hazard e.g. overhead power lines • Safe location of amusement rides away from overhead electrical sources • Event Site inspections to include electrical hazards • Cranes, elevated work platforms and lifting equipment Safe Work Method Statements to include overhead power line check • WA Licenced electrician used for all electrical work at event site • Form 5 to be signed by electrician one hour prior to event commencement • All cords to be tagged and tested • WA Licenced Electrician available on site during event for maintenance and addressing hazards • All generators have inbuilt red safety devices. • All temporary switch boards are protected by approved safety switches • Qualified Senior First Aid Officer on site |  | 5-Severe | E-Rare | Medium | 5 | ALARP
EXAMPLE 3: Event Site | Inadequate Litter Control | • Inefficient cleaning and removal of litter • Insufficient number of bins around venue • Site left unclean after event • Negative impact on the environment | Yes | 2-Minor | D-Unlikely | Low | 4 | • Waste Management Plan • Adequate bins around event site in appropriate and prominent areas • Reputable waste management contractor • Regular consultation with local waste management business and City of Mandurah prior to the event • Event Staff cleaners are provided during the event and post event • Bar and Food area to be maintained and monitored |  | 2-Minor | D-Unlikely | Low | 4 | Yes
EXAMPLE 4: Medical | Weather | • Patrons affected from dehydration, sunburn, heatstroke | Yes | 2-Minor | C-Possible | Medium | 6 | • Sun cream available at event • Adequate shade available and marques and tents positioned to consider path of sun • Communication to event patrons and staff via pre-event bulletins, website, social media to remember to bring sun protection • Staff/volunteers given regular breaks • Adequate drinking water available • First aid officer on site |  | 2-Minor | E-Rare | Low | 2 | Yes
Administration | Excessive Noise | • Noise levels of event exceeds laws and regulations • Complaints from surrounding businesses and residents • Damage to patron's ears • Event closed down
Administration | Ingress/Egress Congestion | • Inadequately organised crowd dispersal methods following event egress • Disruptive and antisocial behaviour • Delay in accessing event
Administration | Security Staff and Crowd Controllers | • Insufficient Security Personnel/Crowd Control • Crowd Controllers not licensed
Administration | Children /Missing Person | • Lost child /Child Abduction • Unable to locate participants or patron • Injury to child • Individual Panic
Administration | Cash Handling | • Theft or loss of money • Armed hold up
Administration | Emergency Exits/Evacuation | • Inadequate number of exits • Exits blocked • Emergency vehicles and personnel unable to access site • Patrons unaware of where exits are located
Administration | Lack of Approvals | • Appropriate approvals not obtained • Event closed down
Administration | Insufficient number of volunteers/staff | • Inadequate supervision of activities • Event activities closed down • Event delayed
Administration | Contractor / Suppliers / Vendors | • Inadequate or no permits, approvals and licenses • Non-compliance with permits, approvals and licenses • Failure to adequately manage and induct
Administration | Unauthorised Traders | • Discontent to other traders • Loss of potential revenue • Annoyance to event goers
Administration | Complaints | • Complaints made to event and local council • Reputational damage to event organisers/sponsor • Event closed down
Administration | Event delay | • Delay in event proceedings • Disgruntled patrons • Anti-social behaviour
Administration | Event cancelled or interrupted | • Failure to carry out event or activities • Inadequate communication about cancellation, • Negative PR • Complaints
Administration | Insurance | • Event not covered by insurance • Event does not have adequate insurance coverage • Suppliers/Contractors do not have adequate insurance coverage
Amusement | Animal Handling / Display | • Animal bite or attack • Uncontrolled animal causing injury to handler or patrons • Patrons contract illness from animals
Amusement | Amusement Rides | • Patrons injured (falls, hit by moving objects, pinch from parts) • Injury to maintenance person during repair or construction of ride • Amusement ride failure/out of action • Ride/Activity not adequately supervised
Amusement | Motor Sports or Driving Display/Aircraft | • Vehicle crashes into barriers/fencing/structure/crowd • Aircraft crash into ground/water/buildings/crowd
Amusement | Contractor / Suppliers / Vendors | • No show/late/cancellation • Inadequate or no clearances, permits, approvals and licences • Unable to source contractor/supplier/vendor
Asset | Turf and Grass Damage | • Damage to turf and grounds due to vehicle movement, installation of structures, • Reticulation activates during event causing damage to property and spraying patrons • Poles erected into ground damage reticulation/below ground services
Asset | Equipment & resources | • Damage to venue/equipment within venue • Damage to surrounding area
Event Site | Slip and Trip Hazards | • Injury to patron from uneven ground, slippery and wet surfaces, objects, curbs, ledges.
Event Site | Sharps/Needles/Syringes/Glass | • Injury or disease transmission via needle or sharp • Sharps left on site after event • Sharps found on site on arrival • Damage to event reputation
Event Site | Water Hazard | • Drowning or submersion • Submerged objects in water
Event Site | Falling objects - tree limbs or fruit | • Injury to patron by a falling object • Damage to asset from falling item
Event Site | Electric Shock or Electrocution | • Overhead power lines - electrocution injuries to staff or participants if machinery or amusement ride contacts overhead power lines • Exposed electrical cables • Electric shock caused by striking underground electrical cable during marquee set up. • Injuries / death to patrons or staff
Event Site | Toilets | • Inadequate toilet facilities • Insufficient number of toilets provided • Non compliance with Council requirements • Illness to patrons
Event Site | Litter Control | • Inefficient cleaning and removal of litter • Insufficient number of bins around venue • Site left unclean after event • Negative impact on the environment
Event Site | Emergency/Ambulance Access | • Inadequate location, design and number of emergency vehicle/ambulance access points • Delayed attendance of emergency services
Event Site | Evacuation | • Failure to evacuate all persons during an emergency
Event Site | Access to facilities for disabled persons | • Facilities unsuitable or insufficient for disabled access • Injury or restricted evacuation • Patrons unable to participate in event
Hazardous Material | Pyrotechnics / Fireworks | • Fire • Complaints from surrounding residents • Injury to spectators (sparks, noise) • Site damaged (grass burnt, buildings damaged) • Weather conditions cause cancellation or delay
Hazardous Material | Storage of Hazardous/Dangerous Goods | • Hazardous material not being maintained in correct manner • Spillage of hazardous material or accident/incident involving hazardous material
Hazardous Material | Fire | • Fire within event site • Personal Injury • Property Damage • Event Cancellation
Human Behaviour | Forklift/Elevated Work Platform | • Accident involving forklift/EVP • Damage to asset by incorrect use of equipment
Human Behaviour | Rigging, Lifting, Cranes | • Accident involving rigging, lifting, crane equipment • Damage to asset by rigging, lifting, crane equipment
Human Behaviour | Crush Injury | • Access around event site constrained • Patron crushed by an object/person
Human Behaviour | Crowd Congestion | • Exceedance of approved and safe patron numbers, overcrowding • Injury to patrons • Unable to safety exit event if required
Human Behaviour | Projectile Objects | • Personal Injury • Property Damage
Human Behaviour | Drug Affected Patron | • Patrons affected by drugs • Anti social behaviour • Injury to other patrons
Human Behaviour | Alcohol Affected Patron | • Patrons affected by alcohol • Anti social behaviour • Injury to other patrons
Human Behaviour | Sexual Misconduct | • Persons engaging in a sexually misconducting manner
Human Behaviour | Disorderly Conduct - Offsite | • Trespassing, antisocial behaviour, noise, disruption, crime • Complaints from surrounding business/landowners • Damage to assets
Human Behaviour | Antisocial Behaviour | • Aggressive, violent, threatening or unsociable behaviour • Person or persons within venue armed or acting in dangerous manner • Damage to reputation • Possibly personal injury and property damage
Human Behaviour | Moshing , Stage Diving and/or Crowd Surfing | • Patrons acting in dangerous manner within crowd • Injury to patrons
Human Behaviour | Mass Evactuation due to Bomb Threat/Attack | • Threat of bomb attack within or near venue • Personal Injury • Property Damage • Event Cancellation
Human Behaviour | Fence Jumping/Trespassing | • Non-ticket holders entering event causing disruption, violence and smuggling contraband • Loss of revenue due to persons not paying to access
Medical | Working/Performing at Heights | • Fall from height causing injury to person or person/s below
Medical | Weather | • Patrons affected from dehydration, sunburn, heatstroke
Medical | Medical Emergency | • Patrons requiring medical emergency medical attention • Lack of available first aid officers • First Aid post not adequately sign posted/easy to locate • Individuals sustain injuries
Medical | Manual Handling | • Incorrect manual handling procedures are used • Injury from incorrect manual handing procedure
Medical | Fatigue Management | • Staff/Volunteer suffers from fatigue
Other | Cooking - Food Vendors/Kitchens | • Contaminated foods consumed by patrons, staff or performers • Allergic reaction • Unsafe food practices • Food poisoning
Technical | Structure Collapse | • Building/structure that has been erected for event collapses • Structure does not meet Australian Standards • Structure blows away and collides with building/patrons
Technical | Site Lighting | • Inadequate lighting and night visibility • No emergency lighting including exit sign lighting
Technical | Electrical Failure | • Electrical failure or loss of power to event • Visibility around event site impacted • Sound, communications systems, refrigeration, artist performance impacted
Technical | Communication Systems | • Failure of communication systems - radios, mobile phone system • Unable to warn people if evacuation is required • Artist performance impacted
Traffic and Transport | Traffic Management and Road Closures | • Inadequate amount of parking causing vehicle congestion and overflow parking impacting on local area/residents • Vehicle/vehicle collisions, pedestrian/vehicle collisions • Traffic from event impacting on local road network causing congestion and risk of vehicle collision • Impact to road users and local road network
Utilities and Services | Food and Beverage | • Insufficient food and drink outlets for patrons • Run out off food or drink • Consumption of alcohol without permits
Utilities and Services | Plumbing Services | • Plumbing failure or sewage not removed causing overflow or spill
Weather | Weather Factors | • Extreme Heat • Electrical storm - Patrons exposed to lightning • Flooding • Wind - Airborne objects, structure collapse • Rain/Hail
Other
Other
Other
Other
Other
Other
Other
Other
Other
Other

## City of Swan Risk Tables (hidden)
| RISK ASSESSMENT MATRIX | [5 empty] | LIKELIHOOD TABLE: LIKELIHOOD OF IMPACT
Consequence
|  | Insignificant | Minor | Moderate | Significant | Severe | Descriptor | Description of Likelihood
Likelihood | Almost Certain | Medium (5) | High (10) | High (15) | Very High (20) | Very High (25) | Almost Certain | The event is expected to occur, more than once a year
| Likely | Low (4) | Medium (8) | High (12) | High (16) | Very High (20) | Likely | The event will probably occur, once a year event
| Possible | Low (3) | Medium (6) | Medium (9) | High (12) | High (15) | Possible | The event should occur, once in 5 year event
| Unlikely | Low (2) | Low (4) | Medium (6) | Medium (8) | High (10) | Unlikely | The event could occur but probably won’t, once in 10 year event
| Rare | Low (1) | Low (2) | Low (3) | Low (4) | Medium (5) | Rare | The event is not expected to occur, once in 20 year event
CONSEQUENCE OF TABLE:SEVERITY OF IMPACT
[7 empty] | Descriptor | Description of Consequence
[7 empty] | Insignificant | No injuries, low financial loss, low reputational damage, insignificant environmental impact
[7 empty] | Minor | First Aid required, medium financial lose, minor impact on event, low profile media attention, minor environmental impact
[7 empty] | Moderate | Medical treatment required, high financial lose, external assistance required, public complaint, moderate environmental impact
[7 empty] | Significant | Extensive injury, major halt to event, major financial loss, emergency services required, high media attention, damage to reputation, significant environmental impact
[7 empty] | Severe | Death, potential prosecution, catastrophic financial loss, irreversible reputational damage, severe environmental impact

## Lists
Likelihood |  |  |  |  | Yes | Yes
A | A-Almost Certain |  |  |  | No | No
B | B-Likely |  |  |  |  | ALARP
C | C-Possible
D | D-Unlikely
E | E-Rare
N/A | N/A
Consequences
5 | 5-Severe
4 | 4-Significant
3 | 3-Moderate
2 | 2-Minor
1 | 1-Insignificant
N/A | N/A
Concatenate | Consequences | Likelihood | Risk Level | Risk Rank
5-SevereA-Almost Certain | 5-Severe | A-Almost Certain | Very High | 25
5-SevereB-Likely | 5-Severe | B-Likely | Very High | 20
4-SignificantA-Almost Certain | 4-Significant | A-Almost Certain | Very High | 20
5-SevereC-Possible | 5-Severe | C-Possible | High | 15
4-SignificantB-Likely | 4-Significant | B-Likely | High | 16
3-ModerateA-Almost Certain | 3-Moderate | A-Almost Certain | High | 15
5-SevereD-Unlikely | 5-Severe | D-Unlikely | High | 10
4-SignificantC-Possible | 4-Significant | C-Possible | High | 12
3-ModerateB-Likely | 3-Moderate | B-Likely | High | 12
2-MinorA-Almost Certain | 2-Minor | A-Almost Certain | High | 10
5-SevereE-Rare | 5-Severe | E-Rare | Medium | 5
4-SignificantD-Unlikely | 4-Significant | D-Unlikely | Medium | 8
3-ModerateC-Possible | 3-Moderate | C-Possible | Medium | 9
2-MinorB-Likely | 2-Minor | B-Likely | Medium | 8
1-InsignificantA-Almost Certain | 1-Insignificant | A-Almost Certain | Medium | 5
4-SignificantE-Rare | 4-Significant | E-Rare | Low | 4
3-ModerateD-Unlikely | 3-Moderate | D-Unlikely | Medium | 6
2-MinorC-Possible | 2-Minor | C-Possible | Medium | 6
1-InsignificantB-Likely | 1-Insignificant | B-Likely | Low | 4
3-ModerateE-Rare | 3-Moderate | E-Rare | Low | 3
2-MinorD-Unlikely | 2-Minor | D-Unlikely | Low | 4
1-InsignificantC-Possible | 1-Insignificant | C-Possible | Low | 3
2-MinorE-Rare | 2-Minor | E-Rare | Low | 2
1-InsignificantD-Unlikely | 1-Insignificant | D-Unlikely | Low | 2
1-InsignificantE-Rare | 1-Insignificant | E-Rare | Low | 1
N/A | N/A | N/A | N/A | N/A
CONTROLS RANKING |  |  |  | Control Rank
PPE | Low |  |  | 1
PPE | Medium |  |  | 2
PPE | High |  |  | 3
Procedures | Low |  |  | 4
Procedures | Medium |  |  | 5
Procedures | High |  |  | 6
Engineering | Low |  |  | 7
Engineering | Medium |  |  | 8
Engineering | High |  |  | 9
Percentage Complete
0%
10%
20%
30%
40%
50%
60%
70%
80%
90%
100%